## Sheet1
PROJECT CHARTER
Project Title | Bikes R US Web Portal Version 1.0 |  |  | Project Manager | Bonnie Joe
Project Start Date | 3rd May 2021 | Project End Date | 30th July 2021 | Project Sponsor | Noor Alani
Business Need
Bikes R Us, requires a website. The primary function of this website will be provide customers with a portal to buy motor bikes and spare parts. The secondary function of this website is to allow users to view history, gallery, "contact us",reviews and "about us" page (all these pages relate to motor bikes).
Project Scope |  |  | Deliverables
To create a platform that users can access information along with buy and sell motor bike parts. More focused on the enthusiast. |  |  | e-commerce website for Bikes R Us online sales to be completed no later than 30th July
Risks and Issues |  |  | Assumptions/Dependencies
Secure contact us system. |  |  | Third-party time contraints
Milestones Schedule
Milestones Schedule |  |  | Target Completion Date | Actual Date
Planning |  |  | 2021-05-10
Design |  |  | 2021-06-10
Implemenation |  |  | 2021-07-15
Test Launch |  |  | 2021-07-16
Final Publishing |  |  | 2021-07-30
Closure of Project |  |  | 2021-07-31
Project Team |  |  | Approval/Review Committee
Project Manager | Bonnie Joe |  | Sponsor | Noor Alani
Technical Lead | Eamon McCabe |  | Business Division Head
Team Members | Bonnie Joe |  | Business Unit Head
| Eamon McCabe |  | Finance Manager | Noor Alani
Noor Alani